## Slide 1: RWANDA SHN Strategy Framework
Water, Sanitation & Hygiene
Deworming
Malaria and other Tropical Diseases
Safe & Secure School Environment
By Denise UWERA and Alice BUMANZI
Tip

## Slide 2
Short Term Action Plan
Water, Sanitation & Hygiene
01
Program Name: | School hygiene and Environmental Health |  |  |  | 
Goal: | To establish and improve healthy and hygienic environment in schools. |  |  |  | 
Needs |  | Activities | Timeframe | Responsible | Verification of Completion
Adequate , clean and separate latrines for girls and Boys available |  | 1.Procure and distribute OSS to all schools | July 2012-December 2012 | MOE MINECOFIN MINALOC COMMUNITIES UNICEF | Number of schools using OSS to clean their latrines
Provision of running and potable drinking water |  | Sensitize schools and communities to use water tanks for raining water harvesting and on use of sur’eau (Chrolination) for drinking water . | September 2012- July 2013 | MOE MININFRA DISTRICTS COMMUNITIES | Number of schools sensitized
Improved hygienic and safe school environment |  | Develop and disseminate integrated BCC messages on proper hygiene in schools. | August 2012-December 2012 | MOE | BCC messages developed , disseminated and available in schools
 |  | 2. Sensitize schools to adopt liquid soap for hand washing and cleaning. | July 2012- June 2012 | MOE | Number of schools sensitized
 |  | 3. Conduct joint monitoring visits on comprehensive hygiene and sanitation in schools. | October 2012 | MOE MOH | Number field visits conducted
 |  | Sensitize ,students, teachers , PTA parents and communities on importance of their participation in schools health and hygiene activities | September – December 2012 | MOE MINALOC | Report for the Sensitization campaign available

## Slide 3
Deworming
02
Short Term Action Plan
Program Name: | Health Promotion and prevention of communicable and non communicable diseases in schools |  |  |  | 
Goal: | To prevent communicable and non-communicable diseases through health promotion and health Education in school children and School Staff |  |  |  | 
Needs |  | Activities | Timeframe | Responsible | Verification of Completion
Assess impact of deworming program on academic performance and health outcomes of school children |  | 1.Develop the concept note and project proposal 2. Engage government and other stakeholders for resources mobilization | July-September2012 | MOE MOH WHO | 1.The proposal available 2.Government and other stakeholders engaged to support the activity
Community awareness on the importance of monitoring deworming program |  | Organize media events (conference, radio,TV) to raise awareness of students, Teachers and communities on the assessment 2. Organize community durbar and participatory workshops | September 2012- December 2012 |  | 1.Number of media events organized 2.Number of community participation workshop and durbar organized
DEWORMING

## Slide 4
DEWORMING CONT’
Water, Sanitation & Hygiene
01
Program Name: | Health Promotion and prevention of communicable and non communicable diseases in schools |  |  |  |  | 
Goal: |  |  | To prevent communicable and non-communicable diseases through health promotion and Education |  |  | 
Needs |  | Activities |  | Timeframe | Responsible | Verification of Completion
Launching pre - deworming activities |  | 1.Develop the proposal 2. Engage government and other stakeholders for resources mobilization 3.Elaborate a joint operation plan in collaboration with MOH 4. Elaboration of monitoring tools 5. Organize training for health care providers and teachers |  | August 2012–March 2013 | MOE MOH | The concept note developed and available Government and other stakeholders engaged to support the activity Joint operational plan developed and available Number of health care providers and teachers trained
Trained teachers on deworming, child growth and nutrition status monitoring. |  | Harmonize the School health training module by integrating issues of deworming, child growth and nutrition status monitoring. Organize in -service training for teachers on comprehensive school health including deworming, child growth and nutrition status monitoring.. Harmonize and disseminate monitoring tools for deworming and nutrition monitoring |  | August 2012–June 2013 | MOE REB MOH | 1.SHT module harmonized 2.Number of in-service teachers trained 3.Monitoring tools harmonized and disseminated in schools
Beyond deworming activities |  | Review SH minimum package guidelines and integrate toilet papers in the sanitation package. Sensitize schools to adopt the use of liquid soap for hand washing Develop and disseminate BCC messages on proper hygiene and nutrition in schools. Conduct joint monitoring and sensitization visits on comprehensive hygiene and sanitation in schools. Sensitize ,students, teachers , PTA parents and communities on importance of their participation in schools health activities |  | September 2012-March 2013 | MOE MOH | 1.SH guidelines reviewed and integrate sanitation facilities 2.Number of schools using liquid soap 3.BCC messages developed ,disseminated and available in schools 4.Number of schools visited during joint monitoring visits 5. Number of sensitization sessions organized

## Slide 5
03
Short Term Action Plan
Program Name: | Health Promotion and prevention of communicable and non communicable diseases |  |  |  | 
Goal: | To prevent communicable and non-communicable diseases including Malaria through health promotion and Education |  |  |  | 
Needs |  | Activities | Timeframe | Responsible | Verification of Completion
Strengthened existing malaria preventive measures in schools |  | 1. Conduct sensitization campaign on malaria prevention and control with emphasize on proper use of treated mosquito nets and maintain a clean environment | July-December | MoH MoE | Number of schools sensitized
 |  | 2.Organise open day activities on malaria prevention trough danses, poems, songs,… in schools | August 2012 | MOE | Number of students participated Reports of activities
 |  | 3.Develop and disseminate IEC materials on Malaria prevention | September | MOE MOH | IEC materials available in schools
 |  | 3.Implement protocols on clean environment in order to eradicate plasmodium in schools | September-December 2012 | MOE MOH | Number of schools implement that protocol
 |  | 4. Develop and disseminate protocol on students participation in school hygiene around schools | November 2012 | MOE | Protocol is available
 |  | 5. Organize workshops of health school teachers on protocols used in malaria eradication and help them to develop their action plans | Nov.-january 2013 | MOE MOH | Number of teachers trained Number of schools raised awereness
Malaria and other Tropical Diseases

## Slide 6
School Environment
04
Short Term Action Plan
Program Name: | SCHOOL ENVIRONMENT |  |  |  | 
Goal: | To establish improved hygienic and healthy environment in schools |  |  |  | 
Needs |  | Activities | Timeframe | Responsible | Verification of Completion
Established conducive learning environment |  | Disseminate national guidelines on school greening and beautification | December 2012 | MOE | Number of schools implementing school greening and beautification guidelines
 |  | Organize and conduct Sensitization campaign through sports competition to implement the national Anti-drugs abuse guidelines | September 2012- November 2012 | MOE MOH MINIYOUTH | Number of Sensitization sessions organized through sports competition
 |  | Disseminate school infrastructure norms, standards and guidelines | September | MOE | School infrastructure norms, standards and guidelines available in schools
 |  | Integrate a component of OVCs support and consideration in to the national school health policy , strategic plan and guidelines | July 2012 | MOE | Policy and guidelines integrate OVC s component
Availability of power in all schools |  | Develop a project proposal and Conduct a rapid assessment I on power availability n schools | December 2012 | moe | Number of schools without power
 |  | Engage government and other stakeholder in resources mobilization | January 2013 | Moe Mininfra minecofin | Resources mobilized
Extension of one laptop per child programme |  | Organize meeting of donors for Advocating for financial support | August 2012 | MOE | Number of donors committed funds