## Sheet1
NIGERIA: NATIONAL PLAN OF ACTION FOR SCHOOL HEALTH PROGRAMMES -
s/n | Strategy | Activity | Sub-activities | Responsible Organisation | Timeline
|  | REPORT WRITING. | share report wih Ministry of Education. | FMOH | 2 Weeks
|  | vBRIEFING OF THE TWG ON SHN | Hold a- one day TWG meeting | FMOE | July- Sep 2012
|  | BUILD CAPACITY OF STATE SHP DESK OFFICERS | Do a 5-day training for state SHP Desk officers on the provision of school health services | FMOE/FMOH | 2012-2013
|  | SCALE UP SCHOOL FEEDING PROGRAMME ACROSS THE COUNTRY | . Select 12 (2/Geo-political zones) staes for pilot . Set up Various school feeding committee (steering, monitoring & evaluation, school-based management) . . Empowere various Committees to implement school feeding programme (developm menu list, aggree on the cost/child, determine sources of funding, employ cooks, sensitization and involvement of Parent association, ) | FMoE/SMoE | 2012-2014
|  | STRENGHTENING SHP NATIONWIDE | Train Teachers, students, food handlers, health workers, head teschers in 12 states. | FMOH/FMOE | July- Sep 2012
|  | FEEDBACK of meeting outcome TO THE AGENCY | Send copy of Report/ feedback SMoH | SMOH | 2 WEEKS
|  | ORGANISE A STAKEHOLDERS MEETING | Hold a- one day Stakeholders meeting | SMOH | July- Sep 2012
|  | ADVOCACY TO STATE EXECUTIVE COUNCIL | Develop advocacy tools,Pay advocacy visits to State Executive council. | SMOH/SMoE | July- Sep 2012
|  | INAUGURATE STATE TECHNICAL WORKING GROUP | Organise a Stake holders meeting to inaugurate the TWG | SMOH
|  | Adoption/production,and Domiciliation of the National SH policy/guideline | Organise a 3-day Stake holders meeting to adopt and domiciliate SH policy and guideline. | SMoE. | Oct- Dec 2012
|  | Dissemination/Orientation of TWG Members on SH policy implementation |  | SMoE. | Jan- March 2013
|  | Capacity building for all school Health workers/ Teachers/Students/food handlers/Head of schools L.G Coordinators | Organise a- 5- day TOT Workshop on thye provision of SH Services. | SMOH/SMoE | April- June 2013.
Roll out plans
| SCREENING FOR HEALTH PROBLEMS | )PRE ENTRY MEDICAL SCREENING - GENOTYPE BLOOD GROUPING TUBERCULOSIS MALARIA ECTOPARASITE e.g Lice infestation PCV ENDOPARASITEe.g worm infestation ANTHROPOMETRY CHEST XRAY | Strenghening Pre entry medical screening. | SMOH | Annually.
|  | A. ROUTINE MEDICAL SCREENING Re- orientation of Health workers and Health teachers on: General body inspection(Hygiene) Ectoparasite e.g Lice Anaemia and other nutrition related diseases. Sanitation B. PERIODIC MEDICAL SCREENING: Nutritional status /growth monitoring through height and weight monitoring Eye screening Dental screening PCV. | Conduct a day training to re orientate the H/W,Teachers on general body hygiene. | SMOH/SMoE | Annually.
PROVIDING SIMPLE AND EASY TO ADMINISTER MEDICATIONS/TREATMENT: DEWORMING Capacity building for teachers TREATMENT OF MINOR AILMENTS Establishment of school Health clinics/Bays First Aid boxes for all schools Provision of essential drugs C. SUPPLEMENTS FOR Vitamin A Deficiency VAD Iron deficiency anaemia IDA Protein-energy malnutrition PEM D. VACCINES Oral polio vaccines OPV Tetanus toxoid TT Health education
| REFERRAL | Strengthen the existing referal system | Develop a referral form and network. | FMOH | 2012-2013
|  | Establishment of school health clubs Health education | Establish school health clubs in all schools | FMoE | On-going
| WATER AND SANITATION | Ensure availability of Water Hand washing facilities Waste and sewage disposal facilities | . Conduct needs assessment on water and sanitation in all schools . Pay advocacy to Ministry of water resources and Environment . Provide WASH equipments |  | 2012-2013