COUNTRY: NIGERIA FOCUSING ON WASH.

| Narrative Summary | Verifiable Indicators | Means of Verification | Critical Assumption |
| --- | --- | --- | --- |
| Impact/ Goal: Improved health status of school children for high academic achievement with 80% by 2015. | No of trained teachers using IEC materials; % of schools using Gender-sensitive latrines and Urinary; Decreased % of referral cases. % of pupils with higher academic performance by 2015. | Reports, data, Annual National Schools Result. | Annual budget will be released on time. Development partners will support. |
| Outcome/Objective: Reduced incidence of childhood diseases with 80% in primary schools by 2015. | % of referral cases | Reports, data, Annual Health abstract. | The Minister of Education will give priority to WASH activities in schools |
| Output/Result: -WASH activities established in primary schools with 80% by 2015. | No of teachers trained on use of IEC materials; No of Pupils washing hand s, using toilets and Urinary 100% correctly. | Reports, data, Annual Health abstract. | The contractors will construct very solid gender sensitive toilets, Urinary and also put hand washing facilities in place according to WHO, UNICEF and World Bank specifications. |
| Activities: 1. Convening Stakeholders meeting to discuss WASH activities in schools. 2. Mapping of schools with regards to WASH activities. 3. Assessing whether the schools involved demonstrated any significant change. 4. Identifying gaps and discussions with stakeholders on the WAY FORWARD to re-establish WASH in schools. 5. Capacity- building of implementers on WASH activities. | No of meetings held and a WAY FORWARD concluded to re- establish WASH activities in schools; No of schools visited and mapped out; No of working materials distributed. No of personnel trained. | Annual Reports and data collected | Funds will be available. Existing WASH schools will not demonstrate any significant change. |
| Inputs/Resources Required: -Human Resources-Personnel/ Consultants; Funds, Training materials. | No of vehicles provided Funds provided. No of Personnel involved. No of Resource materials provided | Reports, Data | Funds will be provided from the National budget. |