| Goal: Improve Health and Education Status of School Children |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| I/ Health and Nutrition Related Policy |  |  |  |  |  |  |  |
| Narrative Summary | Verifiable Indicators |  | Means of Verification |  |  | Critical Assumption |  |
| Out Come: Enhanced quality basic education | Students academic results, |  | National learning assessment , exam Records |  |  | Commitment by GVT, |  |
| Out Puts: - SHN policy designed - Guideline developed | - Policy document produced, guideline developed, |  | Availability of the documents |  |  |  |  |
| Activities: - Policy need assessment on SHN - Provision of training - Development of guidelines and training modules - Disseminating the policy and guidelines | -Reports, trainings conducted, documents produced, number of actors receiving the documents |  | Documents, records |  |  | Implementation/commitment |  |
| In puts: Fund, human resources, trainings, logistics, | Amount of fund available, staff involved, availability of required materials( vehicles, modules…etc) |  | MoFED, MoE, Development Partners |  |  | Lack of budget |  |
| II/ School Based Health & Nutrition Services |  |  |  |  |  |  |  |
| Out Come: Improved students’ health and nutrition status |  | Reduced the Prevalence of morbidity, |  | Students Records, annual Educational Abstracts, |  |  | Low stakeholders involvements, budgets, |
| Out Puts: Increased the number of students de-wormed, students provided school meals, Increased trained personnel… |  | - |  |  |  |  |  |
| Activities: - Carrying out school based de-worming - Providing school meals - Training of school personnel ( de-worming, eye health, Vitamin A, Iron school meal management) - Providing programme documents - Distribution of bed nets - Supplementation of Vitamin A and Iron - Eye health screening - Developing school demonstration gardening |  | - No of students de-wormed - No of schools and students benefiting from school feeding - No of school personnel trained - No of students supplemented with Vitamin A and Net beds - No of students screened - Food amount distributed - No of demonstration sites established |  | - Activities reported, observations, schools receiving food, |  |  | Resource constraints, sustainability |
| In puts: trainings materials, kits, food items, medication, logistics |  | Availability of training materials, food, kits, drugs, |  | MoH, MoE records, annual reports, assessment results, |  |  | Lack and accuracy of information |
| III/ School Based Health and Nutrition Education |  |  |  |  |  |  |  |
| Outcome: Improved implementation and use of SHN services |  |  |  |  |  |  |  |
| Outputs: -Increased level of community participation, capacity of school personnel enhanced, program sustainability ensured, regular SHN education in place | Level of community engagement and participation, level of school personnel engagement, delivery of SHN education on timeframe allocated |  |  | Assessments, activity reports, observations, school records |  |  |  |
| Activities: - Creating community awareness on SHN - Conducting TOT at regional and zonal education bureaus - Conducting school personnel training - Producing and distribution of Information, Education and Communication (IEC) materials - Establish co-curricular activities (for ex. Clubs) - Enhance intra-school experience sharing - Conducting training for peer to peer educator at school level - Mainstreaming SHN education in the teaching learning process | -No of training sessions conducted and No of community members trained -No of trainers trained -No of school personnel trained -No of IEC materials disseminated -Type of IEC materials disseminated -No of SHN clubs established -No of experience sharing sessions conducted -No of peer educators trained |  |  | Activity reports, assessment reports, school records, observations |  |  | Staff turnover at all levels, school personnel availability |
| Inputs: training materials, logistics, fund, human resources | Inputs availability |  |  | Documents from MoE, MoH, implementing partners |  |  | Lack of joint collaboration, lack of resources |
| IV/ Safe and sanitary school environment |  |  |  |  |  |  |  |
| Outcome: Improved safe and hygienic school environment |  |  |  |  |  |  |  |
| Outputs: Increased number of schools with safe and adequate water and sanitation facilities |  |  |  |  |  |  |  |
| Activities: -Constructing separate B&G latrines -Improving safe drinking water access -Availing and constructing hand washing facilities -Fencing school compound -A forestation of school compound -Providing waste disposal facilities | -No of school latrines constructed -No of water points provided -No of hand washing facilities -No of schools with appropriate fencing -No of schools with …. -No of waste disposal facilities |  |  |  | Reports, observations |  | Fund |
| Inputs: Water and sanitation infrastructure, fund, technical assistance, community involvement (labor) |  |  |  |  |  |  |  |